## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project kickoff, team roles, and repository setup | MUST HAVE | No Dependency | Madhumita Kanaparthy | 3- Completed
S1 | S1 | US-002 | Workflow creation and architecture design document | MUST HAVE | LucidChart | Madhumita Kanaparthy | 3- Completed
S1 | S1 | US-003 | Introduction to Streamlit and basic UI scaffolding | MUST HAVE | Streamlit | Ewan John Dennis | 3- Completed
S1 | S1 | US-004 | Introduction to FastMCP and backend communication | MUST HAVE | FastMCP | Abhinav Mehta | 3- Completed
S1 | S1 | US-005 | Environment setup and dependency management (req.txt) | MUST HAVE | Python | Sathish Konatham | 3- Completed
S1 | S1 | US-006 | SerpAPI integration for Google Search data | MUST HAVE | SerpAPI | Tejasvi Mutyala | 3- Completed
S1 | S1 | US-007 | Wikipedia API integration for supplementary information | SHOULD HAVE | Wikipedia API | Om Patil | 3- Completed
S1 | S1 | US-008 | LangChain prompt engineering and HuggingFace model integration | MUST HAVE | HuggingFace | Abhinav Mehta | 3- Completed
S2 | S2 | US-009 | MCP server (mcp_server.py) implementation | MUST HAVE | FastMCP | Madhumita Kanaparthy | 3- Completed
S2 | S2 | US-010 | AI engine (ai_engine.py) - momentum scoring and trend analysis | MUST HAVE | LangChain | Ewan John Dennis | 3- Completed
S2 | S2 | US-011 | Brand comparison module (compserver.py + compclient.py) | MUST HAVE | SerpAPI | Abhinav Mehta | 3- Completed
S2 | S2 | US-012 | Real-time market data retrieval and processing pipeline | MUST HAVE | SerpAPI | Diva Mariya Binu | 3- Completed
S2 | S2 | US-013 | Chat-based AI assistant module (chat_module.py) | MUST HAVE | LangChain | Kaniganti Praneeth Varma | 3- Completed
S2 | S2 | US-014 | Data visualization with Matplotlib (charts and graphs) | MUST HAVE | Matplotlib | Yasmin Begum D | 3- Completed
S2 | S2 | US-015 | Streamlit frontend - main application layout (app.py) | MUST HAVE | Streamlit | Madhumita Kanaparthy | 3- Completed
S2 | S2 | US-016 | PDF report generation module (pdf_report.py) | SHOULD HAVE | ReportLab | Ewan John Dennis | 3- Completed
S3 | S3 | US-017 | End-to-end integration: UI → MCP server → AI engine → display | MUST HAVE | FastMCP | Madhumita Kanaparthy | 3- Completed
S3 | S3 | US-018 | Debug utilities (debug_mcp.py) and error handling | MUST HAVE | Python | Abhinav Mehta | 3- Completed
S3 | S3 | US-019 | Multi-agent workflow: news, competitor, and financial agents | MUST HAVE | LangChain | Ewan John Dennis | 3- Completed
S3 | S3 | US-020 | User query input and result rendering in Streamlit | MUST HAVE | Streamlit | Uday Kumar TC | 3- Completed
S3 | S3 | US-021 | AI-generated strategic insights and recommendations | MUST HAVE | LangChain | Ateendra Pratap Solanki | 3- Completed
S3 | S3 | US-022 | dotenv environment variable management and API key security | MUST HAVE | python-dotenv | Rimsha Tahreem | 3- Completed
S3 | S3 | US-023 | Unit testing and QA for MCP server and AI engine | SHOULD HAVE | pytest | Pamidi Uday | 3- Completed
S3 | S3 | US-024 | README documentation and project summary | MUST HAVE | Markdown | Madhumita Kanaparthy | 3- Completed
S4 | S4 | US-025 | Competitor analysis: price, ratings, product detail comparison | MUST HAVE | SerpAPI | Abhinav Mehta | 3- Completed
S4 | S4 | US-026 | Trend frequency analysis and pattern detection | MUST HAVE | Python | Ewan John Dennis | 3- Completed
S4 | S4 | US-027 | Shopping data retrieval via SerpAPI Google Shopping | SHOULD HAVE | SerpAPI | Logapriya Jothimaniyan | 3- Completed
S4 | S4 | US-028 | Responsive Streamlit dashboard UI improvements | SHOULD HAVE | Streamlit | Aaisha Asif PM | 3- Completed
S4 | S4 | US-029 | Final integration testing and bug fixes | MUST HAVE | Python | Madhumita Kanaparthy | 3- Completed
S4 | S4 | US-030 | Future scope planning: cloud deployment and user auth | COULD HAVE | No Dependency | Sathish Konatham | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | T-001 | Set up GitHub repository and project structure | 2026-02-03 | 2026-02-16 | Madhumita Kanaparthy | Development | 3- Completed | 3 | Day 1: 1; Day 2: 0.5; Day 3: 1; Day 4: 0.5
US-001 | T-002 | Create architecture workflow diagram | 2026-02-03 | 2026-02-16 | Madhumita Kanaparthy | Design | 3- Completed | 2 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5
US-001 | T-003 | Define team roles and sprint plan | 2026-02-03 | 2026-02-16 | Madhumita Kanaparthy | Documentation | 3- Completed | 2 | Day 1: 1; Day 2: 0.5; Day 3: 0.5
US-001 | T-004 | Scaffold Streamlit UI with navigation | 2026-02-03 | 2026-02-16 | Ewan John Dennis | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 1; Day 6: 0.5
US-001 | T-005 | Implement basic page layout and routing | 2026-02-03 | 2026-02-16 | Ewan John Dennis | Development | 3- Completed | 3 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5
US-001 | T-006 | Set up FastMCP server skeleton | 2026-02-03 | 2026-02-16 | Abhinav Mehta | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5; Day 5: 1; Day 6: 0.5; Day 7: 0.5
US-001 | T-007 | Configure .env and dotenv management | 2026-02-03 | 2026-02-16 | Abhinav Mehta | Development | 3- Completed | 2 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5
US-001 | T-008 | Install and configure SerpAPI client | 2026-02-03 | 2026-02-16 | Tejasvi Mutyala | Development | 3- Completed | 3 | Day 1: 1; Day 2: 1; Day 3: 0.5; Day 4: 0.5
US-001 | T-009 | Test SerpAPI Google Search endpoint | 2026-02-03 | 2026-02-16 | Tejasvi Mutyala | Testing | 3- Completed | 2 | Day 1: 0.5; Day 2: 1; Day 3: 0.5
US-001 | T-010 | Integrate Wikipedia API for context | 2026-02-03 | 2026-02-16 | Om Patil | Development | 3- Completed | 3 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5
US-001 | T-011 | Research HuggingFace model options | 2026-02-03 | 2026-02-16 | Abhinav Mehta | Research | 3- Completed | 2 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5
US-001 | T-012 | LangChain + HuggingFace pipeline setup | 2026-02-03 | 2026-02-16 | Abhinav Mehta | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 0.5
US-001 | T-013 | Write req.txt and validate environment | 2026-02-03 | 2026-02-16 | Sathish Konatham | Documentation | 3- Completed | 2 | bar: Day 1 to Day 2
US-001 | T-014 | Peer review and code walkthrough S1 | 2026-02-03 | 2026-02-16 | Diva Mariya Binu | Review | 3- Completed | 1.5 | Day 1: 1; Day 2: 0.5
SPRINT 2 BACKLOG
US-009 | T-015 | Implement FastMCP server routes (mcp_server.py) | 2026-02-17 | 2026-03-02 | Madhumita Kanaparthy | Development | 3- Completed | 6 | Day 1: 1; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5; Day 5: 0.5; Day 6: 1; Day 7: 1; Day 8: 1
US-009 | T-016 | Build AI engine momentum scoring logic | 2026-02-17 | 2026-03-02 | Ewan John Dennis | Development | 3- Completed | 6 | Day 1: 1; Day 2: 1; Day 3: 0.5; Day 4: 0.5; Day 5: 1; Day 6: 0.5; Day 7: 1; Day 8: 0.5
US-009 | T-017 | Integrate trend analysis in ai_engine.py | 2026-02-17 | 2026-03-02 | Ewan John Dennis | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 0.5; Day 5: 0.5; Day 6: 0.5
US-009 | T-018 | Build compserver.py for brand comparison | 2026-02-17 | 2026-03-02 | Abhinav Mehta | Development | 3- Completed | 5 | bar: Day 1 to Day 5
US-009 | T-019 | Build compclient.py for client-side calls | 2026-02-17 | 2026-03-02 | Abhinav Mehta | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 0.5; Day 3: 1; Day 4: 1; Day 5: 0.5; Day 6: 0.5
US-009 | T-020 | Develop real-time data pipeline | 2026-02-17 | 2026-03-02 | Diva Mariya Binu | Development | 3- Completed | 5 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 0.5
US-009 | T-021 | Implement chat_module.py AI assistant | 2026-02-17 | 2026-03-02 | Kaniganti Praneeth Varma | Development | 3- Completed | 5 | Day 1: 1; Day 2: 0.5; Day 3: 1; Day 4: 1; Day 5: 0.5; Day 6: 0.5; Day 7: 0.5
US-009 | T-022 | Add Matplotlib charts and visualizations | 2026-02-17 | 2026-03-02 | Yasmin Begum D | Development | 3- Completed | 4 | Day 1: 1; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5; Day 6: 0.5
US-009 | T-023 | Build Streamlit main application (app.py) | 2026-02-17 | 2026-03-02 | Madhumita Kanaparthy | Development | 3- Completed | 6 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 0.5; Day 6: 0.5; Day 7: 1; Day 8: 0.5
US-009 | T-024 | Implement PDF report module (pdf_report.py) | 2026-02-17 | 2026-03-02 | Ewan John Dennis | Development | 3- Completed | 4 | Day 1: 1; Day 2: 1; Day 3: 0.5; Day 4: 1; Day 5: 0.5
US-009 | T-025 | Unit test chat module | 2026-02-17 | 2026-03-02 | Uday Kumar TC | Testing | 3- Completed | 2 | bar: Day 1 to Day 2
US-009 | T-026 | Unit test AI engine scoring | 2026-02-17 | 2026-03-02 | Rimsha Tahreem | Testing | 3- Completed | 2 | bar: Day 1 to Day 2
US-009 | T-027 | Integration test MCP server with UI | 2026-02-17 | 2026-03-02 | Ateendra Pratap Solanki | Testing | 3- Completed | 3 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5; Day 5: 0.5; Day 6: 0.5
US-009 | T-028 | Code review Sprint 2 deliverables | 2026-02-17 | 2026-03-02 | Madhumita Kanaparthy | Review | 3- Completed | 2 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5
SPRINT 3 BACKLOG
US-017 | T-029 | Full end-to-end integration: UI → MCP → AI → display | 2026-03-03 | 2026-03-16 | Madhumita Kanaparthy | Integration | 3- Completed | 6 | Day 1: 1; Day 2: 0.5; Day 3: 1; Day 4: 1; Day 5: 0.5; Day 6: 0.5; Day 7: 1; Day 8: 0.5
US-017 | T-030 | Implement debug_mcp.py for server diagnostics | 2026-03-03 | 2026-03-16 | Abhinav Mehta | Development | 3- Completed | 4 | Day 1: 1; Day 2: 1; Day 3: 0.5; Day 4: 0.5; Day 5: 1
US-017 | T-031 | Add error handling and fallback responses | 2026-03-03 | 2026-03-16 | Abhinav Mehta | Development | 3- Completed | 3 | bar: Day 1 to Day 3
US-017 | T-032 | Build multi-agent pipeline (news + competitor agents) | 2026-03-03 | 2026-03-16 | Ewan John Dennis | Development | 3- Completed | 6 | 1 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
US-017 | T-033 | Implement chief agent for aggregation | 2026-03-03 | 2026-03-16 | Ewan John Dennis | Development | 3- Completed | 4 | Day 1: 1; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5; Day 6: 0.5
US-017 | T-034 | Render query results in Streamlit UI | 2026-03-03 | 2026-03-16 | Uday Kumar TC | Development | 3- Completed | 3 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5; Day 5: 1
US-017 | T-035 | AI strategic insights generation module | 2026-03-03 | 2026-03-16 | Ateendra Pratap Solanki | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5; Day 6: 1
US-017 | T-036 | dotenv security audit and key rotation | 2026-03-03 | 2026-03-16 | Rimsha Tahreem | Development | 3- Completed | 2 | bar: Day 1 to Day 2
US-017 | T-037 | Write unit tests for all modules | 2026-03-03 | 2026-03-16 | Pamidi Uday | Testing | 3- Completed | 4 | Day 1: 1; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 1
US-017 | T-038 | Write comprehensive README.md | 2026-03-03 | 2026-03-16 | Madhumita Kanaparthy | Documentation | 3- Completed | 3 | bar: Day 1 to Day 3
US-017 | T-039 | Sprint 3 bug fix and regression testing | 2026-03-03 | 2026-03-16 | Abhinav Mehta | Testing | 3- Completed | 3 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5
US-017 | T-040 | Performance review and optimization | 2026-03-03 | 2026-03-16 | Ewan John Dennis | Review | 3- Completed | 2 | bar: Day 1 to Day 2
SPRINT 4 BACKLOG
US-025 | T-041 | Implement price/rating/product comparison logic | 2026-03-17 | 2026-03-30 | Abhinav Mehta | Development | 3- Completed | 5 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 1; Day 5: 0.5; Day 6: 0.5; Day 7: 1; Day 8: 0.5
US-025 | T-042 | Trend frequency and pattern detection module | 2026-03-17 | 2026-03-30 | Ewan John Dennis | Development | 3- Completed | 5 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 0.5; Day 5: 1; Day 6: 0.5; Day 7: 0.5
US-025 | T-043 | SerpAPI Google Shopping endpoint integration | 2026-03-17 | 2026-03-30 | Logapriya Jothimaniyan | Development | 3- Completed | 4 | Day 1: 1; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5; Day 5: 1; Day 6: 0.5
US-025 | T-044 | Streamlit UI responsiveness and UX improvements | 2026-03-17 | 2026-03-30 | Aaisha Asif PM | Development | 3- Completed | 4 | Day 1: 0.5; Day 2: 0.5; Day 3: 1; Day 4: 1; Day 5: 0.5; Day 6: 0.5
US-025 | T-045 | Final integration and system testing | 2026-03-17 | 2026-03-30 | Madhumita Kanaparthy | Testing | 3- Completed | 5 | Day 1: 0.5; Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 0.5; Day 6: 1
US-025 | T-046 | Performance benchmarking and optimization | 2026-03-17 | 2026-03-30 | Ewan John Dennis | Testing | 3- Completed | 3 | bar: Day 1 to Day 3
US-025 | T-047 | Cloud deployment scoping document | 2026-03-17 | 2026-03-30 | Sathish Konatham | Documentation | 3- Completed | 2 | Day 1: 0.5; Day 2: 0.5; Day 3: 0.5; Day 4: 0.5
US-025 | T-048 | User authentication future-scope design | 2026-03-17 | 2026-03-30 | Abhinav Mehta | Design | 3- Completed | 2 | Day 1: 0.5; Day 2: 1; Day 3: 0.5
US-025 | T-049 | Final code cleanup and linting | 2026-03-17 | 2026-03-30 | Tejasvi Mutyala | Development | 3- Completed | 2 | Day 1: 0.5; Day 2: 1; Day 3: 0.5
US-025 | T-050 | Final README and project demo prep | 2026-03-17 | 2026-03-30 | Madhumita Kanaparthy | Documentation | 3- Completed | 3 | Day 1: 0.5; Day 2: 1; Day 3: 0.5; Day 4: 1
US-025 | T-051 | Stakeholder presentation prep | 2026-03-17 | 2026-03-30 | Madhumita Kanaparthy | Documentation | 3- Completed | 2 | Day 1: 1; Day 2: 0.5; Day 3: 0.5
US-025 | T-052 | Final QA sign-off | 2026-03-17 | 2026-03-30 | Abhinav Mehta | Review | 3- Completed | 2 | Day 1: 0.5; Day 2: 1; Day 3: 0.5
Note on D1: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E1: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I2: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J2: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K2: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L2: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M2: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N2: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O2: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P2: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q2: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R2: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S2: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T2: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U2: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V2: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W2: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | 1 | Team unable to access SerpAPI - rate limit hit | Switched to free tier key and implemented retry logic
S1 | 3 | HuggingFace model download too slow on dev machines | Used smaller distilbert model for development, swap to full for prod
S1 | 5 | LangChain version conflict with HuggingFace | Pinned versions in req.txt; resolved by Ewan
S2 | 2 | MCP server not receiving Streamlit requests | Fixed port mismatch; Abhinav updated config
S2 | 4 | AI engine producing inconsistent momentum scores | Madhumita normalized scoring function
S2 | 6 | PDF report generation failing on Windows machines | Added OS check in pdf_report.py; Ewan fixed path separators
S3 | 1 | Chat module response latency too high (>5s) | Switched to async calls; Ewan parallelized agents
S3 | 3 | Multi-agent pipeline producing duplicate results | Added deduplication logic in chief agent
S3 | 5 | dotenv secrets accidentally committed | Reverted commit, rotated API keys, added .env to .gitignore
S4 | 2 | Shopping data incomplete for niche brands | Added fallback to Wikipedia API; Logapriya handled
S4 | 4 | UI crashes on large result sets | Added pagination and result limit in Streamlit; Aaisha fixed
S4 | 6 | Final demo deployment failing on render.com | Switched to local demo; cloud deployment deferred to future scope

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-03 | 2026-02-16 | Madhumita Kanaparthy | Daily stand-up check-ins for blockers | Waiting too long to flag issues | Architecture-first planning approach | Added daily 15-min blocker sync to team calendar
2 | S1 | 2026-02-03 | 2026-02-16 | Abhinav Mehta | Document API integration steps immediately | Committing untested code to main | Thorough peer review before merge | Created integration checklist in README
3 | S1 | 2026-02-03 | 2026-02-16 | Ewan John Dennis | Parallelize API calls to reduce latency | Over-engineering early prototypes | Clean modular code structure | Refactored Streamlit routing to be component-based
4 | S1 | 2026-02-03 | 2026-02-16 | Sathish Konatham | Keep req.txt updated after each install | Ignoring dependency version conflicts | Clear environment documentation | Added version pinning for all dependencies
5 | S1 | 2026-02-03 | 2026-02-16 | Tejasvi Mutyala | Write API integration tests before demo | Assuming APIs work without testing | Testing integrations early | Added SerpAPI smoke tests to Sprint 2 plan
6 | S2 | 2026-02-17 | 2026-03-02 | Madhumita Kanaparthy | Code walkthroughs before end of sprint | Leaving integration until last day | Consistent sprint goal setting | Moved integration task to day 10 of Sprint 3
7 | S2 | 2026-02-17 | 2026-03-02 | Abhinav Mehta | Use async patterns for MCP server calls | Synchronous blocking calls causing UI lag | Modular server design | Converted compserver.py to async; latency reduced by 60%
8 | S2 | 2026-02-17 | 2026-03-02 | Ewan John Dennis | Profile AI engine before optimization | Premature optimization without profiling | Documentation alongside code | Added timing logs to ai_engine.py
9 | S3 | 2026-03-03 | 2026-03-16 | Madhumita Kanaparthy | Sprint demos with full team participation | Skipping demo reviews | Cross-team knowledge sharing | Organized end-of-sprint demo session for all 15 members
10 | S3 | 2026-03-03 | 2026-03-16 | Abhinav Mehta | Automated linting in CI pipeline | Manual code style enforcement | Strict code review standards | Added flake8 to pre-commit hooks
11 | S3 | 2026-03-03 | 2026-03-16 | Ewan John Dennis | Write docstrings for all agent modules | Shipping undocumented functions | Agent-based architecture pattern | Added docstrings to all agent files in Sprint 4
12 | S4 | 2026-03-17 | 2026-03-30 | Madhumita Kanaparthy | Plan cloud deployment from Sprint 1 | Last-minute deployment attempts | Comprehensive project documentation | Added cloud deployment to future scope section of README
13 | S4 | 2026-03-17 | 2026-03-30 | Abhinav Mehta | Involve all team in final QA | Concentrating testing in key members only | Thorough integration testing | Distributed QA tasks across 6 team members in Sprint 4
14 | S4 | 2026-03-17 | 2026-03-30 | Ewan John Dennis | Add caching layer for repeated API calls | Redundant SerpAPI calls on same query | Performance-aware development | Implemented LRU cache for SerpAPI responses
15 | S4 | 2026-03-17 | 2026-03-30 | Diva Mariya Binu | Contribute to sprint planning discussions | Staying silent during blockers | Consistent daily participation | Took ownership of data pipeline validation in S4